COMPANION DOCUMENT

Thesis Schedule & Effort Plan

Automated Multi-Pitch Occupancy & Booking Verification — Master's Thesis

## Assumptions

- Baseline plan: ~24 weeks (6 months) full-time, ~35 productive hours/week (~840 hours total). Part-time or 16-week variants are noted at the end.

- Overlap is deliberate: writing, data collection, and experiments run in parallel — the week numbers below are start/end spans, not strictly sequential blocks.

- Milestones (M1–M7) are supervisor checkpoints; each has a clear exit criterion so slippage is caught early.

## Work Packages, Effort & Dependencies

| WP | Activity | Weeks | Effort | Deliverable | Depends on |
| --- | --- | --- | --- | --- | --- |
| 0 | Setup, planning, dev container, repo, tooling | 1–2 | ~40 h | Working environment + plan | — |
| 1 | Literature review & protocol/taxonomy design | 1–4 | ~70 h | Related-work draft; approved protocol | WP0 |
| 2 | Multi-venue data collection & labelling (κ check) | 3–9 | ~150 h | Balanced, split-ready dataset | WP1 |
| 3 | Preprocessing pipeline + ablations | 6–10 | ~80 h | Reproducible preprocessing + ROI masks | WP2 |
| 4 | Leakage-free four-model benchmark + stats | 9–13 | ~110 h | Benchmark with CIs & significance tests | WP2,3 |
| 5 | Novel architectures: STAN, fusion, context | 12–18 | ~150 h | Ablated novel modules + results | WP4 |
| 6 | System integration + reconciliation + dashboard | 14–19 | ~120 h | End-to-end system on mock feeds | WP4 |
| 7 | Deployment on Mini-PC + 48-h live validation | 18–21 | ~70 h | Accepted live run | WP6 |
| 8 | Writing, figures, revision, defence prep | ongoing→24 | ~140 h | Submitted thesis + slides | all |

## Milestone Gates

| Milestone | By week | Exit criterion (gate) |
| --- | --- | --- |
| M1 | 4 | Protocol, taxonomy & evaluation design approved by supervisor |
| M2 | 9 | Dataset balanced across classes/conditions and split-ready (grouped) |
| M3 | 13 | Four-model benchmark complete with CIs and significance tests |
| M4 | 18 | At least STAN + one fusion module ablated with significant results |
| M5 | 19 | Full pipeline + reconciliation runs end-to-end on mock feeds |
| M6 | 21 | 48-hour live validation on the Mini-PC accepted with staff |
| M7 | 24 | Thesis submitted; defence deck prepared |

## Schedule at a Glance (each column = 2 weeks; bar = active)

| Work package (weeks →) | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP0 Setup & planning |  |  |  |  |  |  |  |  |  |  |  |  |
| WP1 Literature & protocol |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 Data collection & labelling |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 Preprocessing + ablations |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4 Benchmark + statistics |  |  |  |  |  |  |  |  |  |  |  |  |
| WP5 Novel architectures |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6 Integration + reconciliation |  |  |  |  |  |  |  |  |  |  |  |  |
| WP7 Deployment + live run |  |  |  |  |  |  |  |  |  |  |  |  |
| WP8 Writing & revision |  |  |  |  |  |  |  |  |  |  |  |  |

## Effort Summary, Buffer & Compression

- Total effort: ~840 hours over 24 weeks. The two heaviest packages are data (WP2) and novel architectures (WP5) — protect these first.

- Built-in buffer: weeks 22–24 hold ~2 weeks of slack for slippage, re-runs, and revision; do not fill them with new scope.

- Critical path: WP2 → WP4 → WP5 → WP6 → WP7. Any delay in data collection cascades, so start WP2 as early as possible and in parallel with the literature review.

- 16-week compression option: keep WP0–WP4 and the STAN novelty only; drop fusion/context to the extensions list; shorten data collection to 2–3 venues; run the live validation for 24 h instead of 48 h. This still yields a complete, defensible thesis.

## Weekly Working Cadence (recommended)

- One fixed supervisor check-in per fortnight, aligned to the nearest milestone.

- Keep a running lab notebook: every experiment logged with seed, data version, and result — this is what makes the thesis reproducible and defensible.

- Write continuously: draft each chapter as its work package closes, so WP8 is revision, not first-draft panic.

- Weekly rhythm: ~60% build/experiment, ~25% writing, ~15% reading and analysis.